## process_log
Step | Area | Action | Decision / Reasoning | Outcome
1 | Concept & Early Design | Sketched initial product concept and data flow using Replit | Fast iteration environment allowed rapid experimentation with API structure, ingestion flow, and feature scope before committing to a full repo | Clear MVP definition and validated technical feasibility early
2 | UX & Visual Design | Designed UI layouts and styling system in Figma | Separated visual thinking from implementation; allowed focus on information hierarchy, filters, and readability | Consistent, intentional UI translated cleanly into Tailwind CSS
3 | Project Planning | Selected FastAPI backend and Next.js frontend | Async-first backend suited for scraping workloads; Next.js enabled fast iteration and clean data-driven UI | Modern, scalable full-stack architecture
4 | Database Design | Designed relational schema using async SQLAlchemy (Source, Article, IngestionRun) | Normalised schema supports flexible source management, ingestion tracking, and future embeddings | Robust foundation for ingestion, analytics, and AI retrieval
5 | Backend Setup | Implemented FastAPI app, async DB engine, and session lifecycle | Async stack prevents ingestion bottlenecks and supports concurrent workloads | Production-ready API and ingestion backbone
6 | Frontend Setup | Initialised Next.js app with Stale-While-Revalidate (SWR) and Tailwind CSS | SWR provides efficient client-side caching; Tailwind enables rapid, consistent styling from Figma designs | Responsive, performant UI with minimal boilerplate
7 | Modular Scraper Registry | Built registry-based scraper pattern | Each source encapsulated in its own class; avoids monolithic scraper logic | New sources added with minimal code changes
8 | Ingestion Pipeline | Developed async ingestion pipeline with retries and error handling | Concurrent scraping improves throughput; resilience to partial failures | Reliable ingestion even when sources fail or change
9 | Source Management | Added API + UI to enable/disable sources dynamically | Allows operational control without code changes or redeploys | Flexible source governance from the frontend
10 | Frontend Filtering & Curation | Implemented country, topic, source filters and exclusion logic | Empowers users to tailor news flow to their analytical needs | Highly customisable article views
12 | Adding New Sources | Created DB seeding scripts and scraper registration workflow | Repeatable, low-friction onboarding of additional feeds | Scalable expansion of coverage
13 | Debugging & Workarounds | Handled HTML structure changes, 403s, and ingestion edge cases | Scraping is brittle by nature; defensive coding is essential | Increased system resilience to upstream changes
14 | Frontend / Backend Decoupling | Allowed frontend-level filtering independent of backend ingestion | UI changes shouldn’t require backend redeploys | Faster iteration and experimentation
15 | AI Report & Chatbot Architecture | Integrated LLM-powered chatbot using OpenAI APIs | Combined general-purpose reasoning with domain-specific retrieval for accuracy | Natural-language querying over curated news
16 | RAG System Design | Implemented Retrieval-Augmented Generation using chunked and embedded articles | Articles are split, embedded, and retrieved semantically from the database | Grounded AI responses tied directly to ingested sources
17 | Hybrid AI Reasoning | Mixed general LLM intelligence with retrieved article context | Prevents hallucinations while retaining synthesis and summarisation ability | Analyst-grade answers rather than generic summaries
18 | Deployment | Deployed backend and ingestion pipeline to Railway with env-based config | Cloud deployment enables always-on ingestion and API access | Live, production-accessible system
19 | Documentation & Interview Prep | Produced technical overviews, architecture notes, and process logs | Makes decisions legible to reviewers and interviewers | Clear evidence of engineering judgment and system thinking